## Project Timeline
Solar Power Battery |  |  |  | 2022
|  |  |  | SEP |  |  |  |  | OCT |  |  |  | NOV
Deliverable/Task |  | Responsible | Duration | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
ConOps |  |  | 5 w
| Learn and Understand Problem | All | 2 w
| Research and planing | All | 2 w
| Write ConOps | All | 1 w
Status Update 1 |  |  | 2 w
| Identify sensor vendors and specifications |  | 1 w
| Write FSR | All | 1 w
| Write ICD | All | 1 w
| Order Parts |  | 2 w
| Research Database and Application Development | Nathan Gil | 1 w
| Begin designing converter | Tarik Dawson | 2 w
| Begin designing inverter, research system designs | Clement Ong | 2 w
Status Update 2 |  |  | 3 w
| Order Parts | All
| VSCode with microcontroller | Lauren Lugo | 1 w
| MPPT Design Finalized | Lauren Lugo | 2 w
| Implement transformer into inverter circuit design and test | Clement Ong | 2 w
| Design Website / Android App | Nathan Gil | 1 w
| Multiphase intergrated into converter, begin stability testing | Tarik Dawson | 2 w
Status Update 3 |  |  | 2 w
| Recieve Parts | All | 1 w
| Testing sensors with microcontroller | Lauren Lugo | 2w
| MPPT Code written | Lauren Lugo | 3w
| Inverter design completed | Clement Ong | 3 w
| Begin Altium PCB Design | Clement Ong | 1 w
| Implmement "System Info" (Battery Level, Power, Current, Voltage Outputs, Connected Devices) | Nathan Gil | 3 w
| Implement "Overview" (Power graph, mode, home page) | Nathan Gil | 3 w
| Conveter design complete | Tarik Dawson | 1 w
| Begin Altium PCB Design | Tarik Dawson | 1 w
Status Update 4 |  |  | 2 w
| Testing of Dashboard / System Info using test data | Nathan Gil | 1 w
| Finish breadboard and PCB design | Clement Ong | 2 w
| Finish dsPIC Code | Clement Ong | 2 w
| PCB designed and ordered | Tarik Dawson | 2 w
| MPPT code tested with full circuit design | Lauren Lugo | 2 w
| Conclusion | All | 1 w
| Final presentation | All | 1 w
| Deliverables | All | 1 w
Annotations | [8 empty] | Not Started
Behind Schedule
In Progress
Completed