## Project Timeline
Solar Power Battery |  |  |  | 2022
|  |  |  | January/February | [5 empty] | March |  |  |  | April
Deliverable/Task |  | Responsible | Duration | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-01 | 2023-04-10
Status Update 1
| Discuss PCB Breakdown | All | 2 w
| Review Subsystems | All | 2 w
| Test all sensors and switches | Lauren | 2 w
| Connect to wifi | Lauren | 1 w
| Make PCB for Sensors and Switches | Tarik | 1 w
| Fix Feedback system | Tarik | 1 w
| Fix Firebase Backend by Organizing User Data | Nathan | 1 w
| Finalize inverter design | Clement | 2 w
Status Update 2 |  |  | 2 w
| Make Final Changes to Front-End Design | Nathan | 2 w
| Add Senors and Switch into PCB | Tarik | 1 w
| Order New PCB and Assemble | Tarik/Lauren | 2 w
| Validate Updated Subsystem | Tarik | 1 w
| Connect to Database | Lauren | 2 w
| Update sensor code | Lauren | 2 w
| Finalize MCU Code for PWM | Clement | 3 w
| Test H-bridge | Clement | 2 w
| Build and test full inverter on breadboard | Clement | 3 w
| Order PCB and all parts | Clement | 2 w
Status Update 3 |  |  | 3 w
| Create Design for Backend with Real Time Solar Panel Data | Nathan Gil | 3 w
| Three Way Communication (Backend, Front-End, ESP32) | Nathan Gil | 3 w
| Integrate DC-DC Converter with other subsystems | Tarik | 2 w
| Test Battery Charging with Lauren | Tarik | 3 w
| Check that switches and sensors are working properly on PCB | Lauren | 3 w
| Ensure that the other system are integrate with the switches and sensors | Lauren | 2 w
| Implement deadband gap in MCU | Clement | 1 w
| Solder and begin testing Inverter | Clement | 2 w
Status Update 4 |  |  | 2 w
| Testing, Validation of Real Time Data for the Backend | Nathan Gil | 2 w
| Optimization of Code for Front End (lot of data being processed) | Nathan Gil | 2 w
| Validate with the System | Tarik | 2 w
| Test and Validate ESP PCB | Lauren Lugo | 2w
| Test system in various light settings | Lauren Lugo | 3 w
| Debug and validate Inverter | Clement | 2 w
Status Update 5 |  |  | 2 w
| Last Fixes for the Backend, Frontend, ESP32 | Nathan Gil | 1 w
| Final Debug for Demo | Tarik | 1 w
| Clean up code and run final diagnositcs | Lauren | 1 w
| Integrate inverter with othe subsystems | Clement | 1 w
| Final Checks/Debug for Demo | Clement | 1 w
Annotations | [9 empty] | Not Started
Behind Schedule
In Progress
Completed